## DPR
DRILLING PROGRESS OF RI-IV,NAGPUR
Murpar Camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY |  | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks
RD100-5 | 18 |  | 18 | 0 | 18 | 1819 | 1837 |  | 133.4 | CMWSWC134/27.06.2026 | south of wirur chincholi | coring |  | normal | 0.5 | 10 | 20 | 10
DM-1000-21 | 0 |  | 0 | 0 | 0 | 1323 | 1323 |  |  |  | south of wirur chincholi | coring | 5 | shifting completed,s/l delayed due to rig b/d
RD-100-04 | 19.4 |  | 19.4 | 0 | 19.4 | 1681 | 1700.4 |  | 19.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | coring | 2 | pump safety valve damaged,repaired. | 0.5 | 8 | 20 | 10
Total | 37.4 |  | 37.4 |  | 37.4
DRILLING PROGRESS OF RI-IV,NAGPUR
02.07.2026
Murpar Camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY |  | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks
RD100-5 | 30 |  | 30 | 18 | 48 | 1837 | 1867 | 133.4 | 163.4 | CMWSWC134/27.06.2026 | south of wirur chincholi | coring |  | hard formation | 0.5 | 10 | 20 | 10
DM-1000-21 | 3 |  | 3 | 0 | 3 | 1323 | 1326 | 0 | 3 | CMWSWC136/02.07.2026 | south of wirur chincholi | coring | 5 | rig b/d and repairing done,bearing problem, rpaired. | 0.5 | 5 | 20 | 10
RD-100-04 | 9 |  | 9 | 19.4 | 28.4 | 1700.4 | 1709.4 | 19.4 | 28.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | coring | 4 | mud pump problem,piston rod dmaged,repaired | 0.5 | 6 | 20 | 10
Total | 42 |  | 42 |  | 79.4
DRILLING PROGRESS OF RI-IV,NAGPUR
03.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
TOTAL
RD100-5 | 24 |  | 24 | 48 | 72 | 1867 | 1891 | 163.4 | 187.4 | CMWSWC134/27.06.2026 | south of wirur chincholi | coring |  | hard formation,b/h washed. | 0.5 | 10 | 20 | 10
DM-1000-21 | 19.5 |  | 19.5 | 3 | 22.5 | 1326 | 1345.5 | 3 | 22.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | coring | 6 | hyd chain damaged,repairing done,mud pump b/d. | 0.5 | 4 | 20 | 10
RD-100-04 | 30 |  | 30 | 28.4 | 58.4 | 1709.4 | 1739.4 | 28.4 | 58.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | coring | 4 | mud pump problem,piston rod dmaged,repaired | 0.5 | 6 | 20 | 10
Total | 73.5 |  | 73.5 |  | 152.9 |  | 4975.9
DRILLING PROGRESS OF RI-IV,NAGPUR
04.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
TOTAL
RD100-5 | 9 |  | 9 | 72 | 81 | 1891 | 1900 | 187.4 | 196.4 | CMWSWC134/27.06.2026 | south of wirur chincholi | coring |  | Reached bottom, drilling started,bh closed. | 0.5 | 10 | 20 | 10
DM-1000-21 | 33 |  | 33 | 22.5 | 55.5 | 1345.5 | 1378.5 | 22.5 | 55.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | coring |  | Reached bottom, drilling started, bh washed. | 0.5 | 10 | 20 | 10
RD-100-04 | 15 |  | 15 | 58.4 | 73.4 | 1739.4 | 1754.4 | 58.4 | 73.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | coring |  | Reached bottom, drilling started. Bh washed. | 0.5 | 10 | 20 | 10
Total | 57 |  | 57 |  | 209.9 | [8 empty] | Note : Drilling work hampered due to heavy rain.
DRILLING PROGRESS OF RI-IV,NAGPUR
05.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
TOTAL
RD100-5 | 0 |  | 0 | 81 | 81 | 1900 | 1900 | 196.4 | 196.4 | CMWSWC134/27.06.2026 | south of wirur chincholi | coring | 8 | rig b/d. | 0.5 | 0
DM-1000-21 | 27 | 18 | 45 | 55.5 | 100.5 | 1378.5 | 1423.5 | 55.5 | 100.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | coring |  | normal | 0.5 | 14 | 10 | 10
RD-100-04 | 15 |  | 15 | 73.4 | 88.4 | 1754.4 | 1769.4 | 73.4 | 88.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | coring | 4 | mud pump problem,piston rod dmaged,repaired | 0.5 | 3 | 10 | 20
Total | 42 | 18 | 60 | 209.9 | 269.9 | 5032.9 | 5092.9 | [6 empty] | Note : Drilling work hampered due to heavy rain.
DRILLING PROGRESS OF RI-IV,NAGPUR
06.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
[17 empty] | Rig | Pump
RD100-5 | 0 |  | 0 | 81 | 81 | 1900 | 1900 | 196.4 | 196.4 | CMWSWC134/27.06.2026 | south of wirur chincholi | coring | 10 | shortage of manpower.rig b/d. | 0.5 | 0
DM-1000-21 | 24 |  | 24 | 100.5 | 124.5 | 1423.5 | 1447.5 | 100.5 | 124.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | coring |  | normal | 0.5 | 10 | 20 | 10
RD-100-04 | 21 |  | 21 | 88.4 | 109.4 | 1769.4 | 1790.4 | 88.4 | 109.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | coring | 4 | Mud pump b/d,repaired. | 0.5 | 6 | 20 | 10
Total | 45 | 0 | 45 | 269.9 | 314.9 | 5092.9 | 5137.9 | [6 empty] | Note : Drilling work hampered due to shortage of man power
DRILLING PROGRESS OF RI-IV,NAGPUR
07.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
[17 empty] | Rig | Pump
RD100-5 | 0 |  | 0 | 81 | 81 | 1900 | 1900 | 196.4 | 196.4 | CMWSWC134/27.06.2026 | south of wirur chincholi | coring | 10 | shortage of manpower.rig b/d. | 0.5 | 0
DM-1000-21 | 24 |  | 24 | 124.5 | 148.5 | 1447.5 | 1471.5 | 124.5 | 148.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | coring |  | normal | 0.5 | 10 | 20 | 10
RD-100-04 | 0 |  | 0 | 109.4 | 109.4 | 1790.4 | 1790.4 | 109.4 | 109.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | coring | 10 | mud pump b/d,repairing u/p,arranged another mud pump,s/l delayed due to heavy rain at drill site | 0.5 | 0
Total | 24 |  | 24 | 314.9 | 338.9 | 5137.9 | 5161.9 | [6 empty] | Note : Drilling work hampered due to shortage of man power
DRILLING PROGRESS OF RI-IV,NAGPUR
08.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
[17 empty] | Rig | Pump
RD100-5 | 0 |  | 0 | 81 | 81 | 1900 | 1900 | 196.4 | 196.4 | CMWSWC134/27.06.2026 | south of wirur chincholi | coring | 12 | shortage of manpower.rig b/d. | 0.5 | 0
DM-1000-21 | 21 |  | 21 | 148.5 | 169.5 | 1471.5 | 1492.5 | 148.5 | 169.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | coring |  | normal | 0.5 | 10 | 20 | 10
RD-100-04 | 21 |  | 21 | 109.4 | 130.4 | 1790.4 | 1811.4 | 109.4 | 130.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | coring | 2 | mmd pump setting done. | 0.5 | 10 | 20 | 10
Total | 42 |  | 42 | 338.9 | 380.9 | 5161.9 | 5203.9 | [6 empty] | Note : Drilling work hampered due to shortage of man power
DRILLING PROGRESS OF RI-IV,NAGPUR
09.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
[17 empty] | Rig | Pump
RD100-5 | 0 |  | 0 | 81 | 81 | 1900 | 1900 | 196.4 | 196.4 | CMWSWC134/27.06.2026 | south of wirur chincholi | coring | 12 | shortage of manpower.rig b/d. | 0.5 | 0
DM-1000-21 | 33 |  | 33 | 169.5 | 202.5 | 1492.5 | 1525.5 | 169.5 | 202.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | coring |  | normal | 0.5 | 10 | 20 | 10
RD-100-04 | 27 |  | 27 | 130.4 | 157.4 | 1811.4 | 1838.4 | 130.4 | 157.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | coring | 0 | rrunning | 0.5 | 10 | 20 | 10
Total | 60 |  | 60 | 380.9 | 440.9 | 5203.9 | 5263.9 | [6 empty] | Note : Drilling work hampered due to shortage of man power
DRILLING PROGRESS OF RI-IV,NAGPUR
10.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
[17 empty] | Rig | Pump
RD100-5 | 0 |  | 0 | 81 | 81 | 1900 | 1900 | 196.4 | 196.4 | CMWSWC134/27.06.2026 | south of wirur chincholi | coring | 12 | shortage of manpower.rig b/d. | 0.5 | 0
DM-1000-21 | 24 |  | 24 | 202.5 | 226.5 | 1525.5 | 1549.5 | 202.5 | 226.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | coring |  | normal | 0.5 | 10 | 20 | 10
RD-100-04 | 24 |  | 24 | 157.4 | 181.4 | 1838.4 | 1862.4 | 157.4 | 181.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | coring | 0 | rrunning | 0.5 | 10 | 20 | 10
Total | 48 |  | 48 | 440.9 | 488.9 | 5263.9 | 5311.9 | [6 empty] | Note : Drilling work hampered due to shortage of man power
DRILLING PROGRESS OF RI-IV,NAGPUR
11.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
[17 empty] | Rig | Pump
RD100-5 | 0 |  | 0 | 81 | 81 | 1900 | 1900 | 196.4 | 196.4 |  |  | c | 12 | shortage of manpower.rig b/d. | 0.5 | 0
DM-1000-21 | 24 |  | 24 | 226.5 | 250.5 | 1549.5 | 1573.5 | 226.5 | 250.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | c | 2 | mud pump b/d,repaired. | 0.5 | 8 | 20 | 10
RD-100-04 | 27 |  | 27 | 181.4 | 208.4 | 1862.4 | 1889.4 | 181.4 | 208.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | c | 0 | running | 0.5 | 10 | 20 | 10
Total | 51 |  | 51 | 488.9 | 539.9 | 5311.9 | 5362.9 | [6 empty] | Note : Drilling work hampered due to shortage of man power
DRILLING PROGRESS OF RI-IV,NAGPUR
11.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
[17 empty] | Rig | Pump
RD100-5 | 0 |  | 0 | 81 | 81 | 1900 | 1900 | 196.4 | 196.4 |  |  | c | 12 | Not operated |  | 0
DM-1000-21 | 18 |  | 18 | 250.5 | 268.5 | 1573.5 | 1591.5 | 250.5 | 268.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | c | 0 | running | 0.5 | 6.5 | 10 | 10
RD-100-04 | 18 |  | 18 | 208.4 | 226.4 | 1889.4 | 1907.4 | 208.4 | 226.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | c | 0 | running | 0.5 | 6.5 | 10 | 10
Total | 36 |  | 36 | 539.9 | 575.9 | 5362.9 | 5398.9
DRILLING PROGRESS OF RI-IV,NAGPUR
13.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
[17 empty] | Pump | Rig
RD100-5 | 0 |  | 0 | 81 | 81 | 1900 | 1900 | 196.4 | 196.4 |  |  | c | 12 | rig b/d,repairining u/p,block shifting u/p |  | 0
DM-1000-21 | 24 |  | 24 | 268.5 | 292.5 | 1591.5 | 1615.5 | 268.5 | 292.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | c | 0 | string jammed,released. | 0.5 | 10 | 10 | 20
RD-100-04 | 24 |  | 24 | 226.4 | 250.4 | 1907.4 | 1931.4 | 226.4 | 250.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | c | 0 | running | 0.5 | 10 | 10 | 20
Total | 48 |  | 48 | 575.9 | 623.9 | 5398.9 | 5446.9
DRILLING PROGRESS OF RI-IV,NAGPUR
14.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
[17 empty] | Pump | Rig
RD100-5 | 0 |  | 0 | 81 | 81 | 1900 | 1900 | 196.4 | 196.4 |  |  | c | 12 | rig b/d,repairining u/p,block shifting u/p |  | 0
DM-1000-21 | 27 |  | 27 | 292.5 | 319.5 | 1615.5 | 1642.5 | 292.5 | 319.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | c | 0 | string jammed,released. | 0.5 | 10 | 10 | 20
RD-100-04 | 24 |  | 24 | 250.4 | 274.4 | 1931.4 | 1955.4 | 250.4 | 274.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | c | 0 | running | 0.5 | 10 | 10 | 20
Total | 51 |  | 51 | 623.9 | 674.9 | 5446.9 | 5497.9
DRILLING PROGRESS OF RI-IV,NAGPUR
15.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
[17 empty] | Pump | Rig
RD100-5 | 0 |  | 0 | 81 | 81 | 1900 | 1900 | 196.4 | 196.4 |  |  | c | 12 | rig b/d,repairining u/p,block shifting u/p |  | 0
DM-1000-21 | 15 |  | 15 | 319.5 | 334.5 | 1642.5 | 1657.5 | 319.5 | 334.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | c | 4 | mud pump b/d,repaired. | 0.5 | 6 | 10 | 20
RD-100-04 | 24 |  | 24 | 274.4 | 298.4 | 1955.4 | 1979.4 | 274.4 | 298.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | c | 0 | core slipped,recovered. | 0.5 | 10 | 10 | 20
Total | 39 |  | 39 | 674.9 | 713.9 | 5497.9 | 5536.9
DRILLING PROGRESS OF RI-IV,NAGPUR
16.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
[17 empty] | Pump | Rig
RD100-5 | 0 |  | 0 | 81 | 81 | 1900 | 1900 | 196.4 | 196.4 |  |  | c | 12 | RIG B/D , REPAIRING U/P |  | 0
DM-1000-21 | 12 |  | 12 | 334.5 | 346.5 | 1657.5 | 1669.5 | 334.5 | 346.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | c | 0 | BH JAM AND RELEASED , HEAVY CAVING , BH WASHED | 0.5 | 10 | 10 | 20
RD-100-04 | 15 |  | 15 | 298.4 | 313.4 | 1979.4 | 1994.4 | 298.4 | 313.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | c | 0 | RUNNING VERY HARD FORMATION | 0.5 | 10 | 10 | 10
Total | 27 |  | 27 | 713.9 | 740.9 | 5536.9 | 5563.9
DRILLING PROGRESS OF RI-IV,NAGPUR
17.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
[17 empty] | Pump | Rig
RD100-5 | 0 |  | 0 | 81 | 81 | 1900 | 1900 | 196.4 | 196.4 |  |  | c | 12 | RIG B/D , REPAIRING U/P |  | 0
DM-1000-21 | 12 |  | 12 | 346.5 | 358.5 | 1669.5 | 1681.5 | 346.5 | 358.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | c | 0 | Heavu caving,borehole jammed,and released,difficulty in reaching bottom. | 0.5 | 10 | 10 | 20
RD-100-04 | 15 |  | 15 | 313.4 | 328.4 | 1994.4 | 2009.4 | 313.4 | 328.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | c | 0 | RUNNING VERY HARD FORMATION | 0.5 | 10 | 10 | 10
Total | 27 |  | 27 | 740.9 | 767.9 | 5563.9 | 5590.9
DRILLING PROGRESS OF RI-IV,NAGPUR
18.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
[17 empty] | Pump | Rig
RD100-5 | 0 |  | 0 | 81 | 81 | 1900 | 1900 | 196.4 | 196.4 |  |  | c | 12 | RIG B/D , REPAIRING U/P |  | 0
DM-1000-21 | 9 |  | 9 | 358.5 | 367.5 | 1681.5 | 1690.5 | 358.5 | 367.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | c | 4 | Heavu caving,borehole jammed,and released,difficulty in reaching bottom.mud pump b/d.repaired. | 0.5 | 6 | 10 | 20
RD-100-04 | 18 |  | 18 | 328.4 | 346.4 | 2009.4 | 2027.4 | 328.4 | 346.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | c | 0 | RUNNING VERY HARD FORMATION | 0.5 | 10 | 10 | 10
Total | 27 |  | 27 | 767.9 | 794.9 | 5590.9 | 5617.9
19.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
[17 empty] | Pump | Rig
RD100-5 | 0 |  | 0 | 81 | 81 | 1900 | 1900 | 196.4 | 196.4 |  |  | c | 12 | RIG B/D , REPAIRING U/P |  | 0
DM-1000-21 | 12 |  | 12 | 367.5 | 379.5 | 1690.5 | 1702.5 | 367.5 | 379.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | c | 0 | Heavu caving,difficulty in reaching bottom. | 0.5 | 6 | 10 | 10
RD-100-04 | 15 |  | 15 | 346.4 | 361.4 | 2027.4 | 2042.4 | 346.4 | 361.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | c | 0 | RUNNING VERY HARD FORMATION | 0.5 | 6
Total | 27 |  | 27 | 794.9 | 821.9 | 5617.9 | 5644.9
20.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
[17 empty] | Pump | Rig
RD100-5 | 0 |  | 0 | 81 | 81 | 1900 | 1900 | 196.4 | 196.4 |  |  | c | 12 | RIG REPAIRED, DELAYED BY AMC TEAM IN LOADING IN TRUCK |  | 0
DM-1000-21 | 0 |  | 0 | 379.5 | 379.5 | 1702.5 | 1702.5 | 379.5 | 379.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | c | 12 | PUMP SAFETY VALVE B/D , COMPETENT MECHANIC ABSENT AT SITE | 0.5 | 0 | 20 | 20
RD-100-04 | 15 |  | 15 | 361.4 | 376.4 | 2042.4 | 2057.4 | 361.4 | 376.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | c | 0 | RUNNING VERY HARD FORMATION | 0.5 | 8
Total | 15 |  | 15 | 821.9 | 836.9 | 5644.9 | 5659.9
21.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
[17 empty] | Pump | Rig
RD100-5 | 0 |  | 0 | 81 | 81 | 1900 | 1900 | 196.4 | 196.4 |  |  | c | 12 | RIG SHIFTED , WORK HAMPERED DUE TO HEAVY RAIN , SHORTAGE OF MANPOWER |  | 0
DM-1000-21 | 0 |  | 0 | 379.5 | 379.5 | 1702.5 | 1702.5 | 379.5 | 379.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | c | 12 | PUMP REPAIRED AND AGAIN B/D , COMPETENT MECHANIC ABSENT AT SITE , REPAIRING HAMPERED | 0.5 | 0
RD-100-04 | 15 |  | 15 | 376.4 | 391.4 | 2057.4 | 2072.4 | 376.4 | 391.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | c | 0 | RUNNING VERY HARD FORMATION, SHORTAGE OF MANPOWER | 0.5 | 8 | 10 | 20
Total | 15 |  | 15 | 836.9 | 851.9 | 5659.9 | 5674.9
22.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
[17 empty] | Pump | Rig
RD100-5 | 0 |  | 0 | 81 | 81 | 1900 | 1900 | 196.4 | 196.4 |  |  | c |  | RIG MOUNTED ON CHASSIS , S/L DONE BUT WORK HAMPERED DUE TO RAIN AND SHORTAGE OF MANPOWER | 0.5 | 8
DM-1000-21 | 0 |  | 0 | 379.5 | 379.5 | 1702.5 | 1702.5 | 379.5 | 379.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | c |  | STRING JAM , TRYING TO RELEASE JAM , FAILED , CHARGED STRING , DIFFICULTY IN WORK DUE TO SHOERAGE OF MANPOWER | 0.5 | 0
RD-100-04 | 12 |  | 12 | 391.4 | 403.4 | 2072.4 | 2084.4 | 391.4 | 403.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | c | 0 | TUBE JAM AND RELEASED RUNNING VERY HARD FORMATION, WORK HAMPERED DUE TO SHORTAGE OF MANPOWER AND RAIN | 0.5 | 8
Total | 12 |  | 12 | 851.9 | 863.9 | 5674.9 | 5686.9
23.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
[17 empty] | Pump | Rig
RD100-5 | 0 |  | 0 | 81 | 81 | 1900 | 1900 | 196.4 | 196.4 |  |  | c |  | DERRECK INSTALLED , PUMP SETTING DONE , ROPE DAMAGED , REPAIRED , RAIN AT SITE | 0.5 | 8
DM-1000-21 | 0 |  | 0 | 379.5 | 379.5 | 1702.5 | 1702.5 | 379.5 | 379.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | c | 10 | STRING JAM , POLYMER INJECTED , TRYING TO RELEASE JAM , FAILED , CHARGED STRING AGAIN , SUFFICIENT TENSION NOT GIVEN DUE TO SHORTAGE OF MANPOWER, , MUD PUMP HOSEPIPE BURST , PUMP B/D , AMC TEAM NOT HAVING HOSEPIPE AT SITE | 0.5 | 0 | 20 | 20
RD-100-04 | 12 |  | 12 | 403.4 | 415.4 | 2084.4 | 2096.4 | 403.4 | 415.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | c | 0 | RUNNING , WORK HAMPERED DUE TO SHORTAGE OF MANPOWER | 0.5 | 8 | 10 | 20
Total | 12 |  | 12 | 863.9 | 875.9 | 5686.9 | 5698.9
24.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
[17 empty] | Pump | Rig
RD100-5 | 7.4 |  | 7.4 | 81 | 88.4 | 1900 | 1907.4 | 196.4 | 7.4 | CMWGE386/24.07.2026 | DIPSIDE OF BORDA | c | 4 | NEW BOREHOLE STARTED,MUD PUMP B/D | 0.5 | 6 | 10 | 20
DM-1000-21 | 0 |  | 0 | 379.5 | 379.5 | 1702.5 | 1702.5 | 379.5 | 379.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | c | 10 | STRING JAM , POLYMER INJECTED , TRYING TO RELEASE JAM , FAILED , CHARGED STRING AGAIN , SUFFICIENT TENSION NOT GIVEN DUE TO SHORTAGE OF MANPOWER, , MUD PUMP HOSEPIPE BURST , PUMP B/D , AMC TEAM NOT HAVING HOSEPIPE AT SITE | 0.5 | 0 | 10 | 20
RD-100-04 | 9 |  | 9 | 415.4 | 424.4 | 2096.4 | 2105.4 | 415.4 | 424.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | c | 2 | RUNNING , WORK HAMPERED DUE TO SHORTAGE OF MANPOWER | 0.5 | 8 | 10 | 20
Total | 16.4 |  | 16.4 | 875.9 | 892.3 | 5698.9 | 5715.3
25.07.2026
Murpar camp | Shift |  | Total (m) | Monthly Cumm. Meterage EARLIER DAY | Monthly Cumm. Meterage | Yearly Cumm. Meterage EARLIER DAY | Yearly Cumm. Meterage | BH Depth (m) EARLIER DAY | BH Depth (m) | BH ID / Start dt | Block Name | BH Type | B/D Hours.Minutes | Remarks | PREVENTIVE MAINTENANCE | Working Hour | HSD
[17 empty] | Pump | Rig
RD100-5 | 9 |  | 9 | 88.4 | 97.4 | 1907.4 | 1916.4 | 7.4 | 16.4 | CMWGE386/24.07.2026 | DIPSIDE OF BORDA | c | 4 | MUD PUMP B/D,REAPAIRED. | 0.5 | 6 | 10 | 20
DM-1000-21 | 0 |  | 0 | 379.5 | 379.5 | 1702.5 | 1702.5 | 379.5 | 379.5 | CMWSWC136/02.07.2026 | south of wirur chincholi | c | 10 | STRING JAM , POLYMER INJECTED , TRYING TO RELEASE JAM , FAILED , CHARGED STRING AGAIN , SUFFICIENT TENSION NOT GIVEN DUE TO SHORTAGE OF MANPOWER, , MUD PUMP HOSEPIPE BURST , PUMP B/D , AMC TEAM NOT HAVING HOSEPIPE AT SITE | 0.5 | 0 | 10 | 20
RD-100-04 | 9 |  | 9 | 424.4 | 433.4 | 2105.4 | 2114.4 | 424.4 | 433.4 | CMWSWC135/01.07.2026 | south of wirur chincholi | c |  | BOREHOLE CLOSED.HARD FORMATION | 0.5 | 8 | 10 | 20
Total | 18 |  | 18 | 892.3 | 910.3 | 5715.3 | 5733.3